Cobb Bench – To Do List

* 4/15 PTO meeting – present ideas
* Come up with project name!

Research/Planning

Read “How-to” on Cobb

Alternative methods

Contact those who have built Cobb

Meet with Tom Horn (Edison Principal)

Where do you get Cobb?

Material acquisition

SketchUp Bench

Take measurements

Design bench – sketch various ideas

Create SketchUp

Create JPG’s of different angles to present

Create Dates

Plan out days to build

Garden Club – help with planning/designing/building

Art classes – Tiles?

Create Calendar for Volunteers

Volunteers

Contact Edison, University, JSMA and other key contacts to source volunteers

Write up photography/video releases

Other forms? Liability?

Building

* how to block off area on playground while in progress. Should try to build in one weekend? One week?

Install Art/Finishing Touches

Install tiles

Paint/Finish

Evaluation/Finalization

Opening Event for finished Cobb

Survey for volunteers

Record successes and failures

Week 1 – Research/Planning

Week 2 – Research/Planning, SketchUp Bench

Week 3 – SketchUp Bench, Create Dates

Week 4 - Volunteers

Week 5 - Building

Week 6 - Building

Week 7 – Install art/Finishing touches

Week 8 – Evaluation Finalization